## Task Timeline
Departure Day +/- | Translation | Task | Owners | Resources
D-Day -90 | 3 months before | Present preliminary plans at PLC meeting Bookings and deposits for campsite and event vendors Recruit Trip Committee members and adult drivers Book BMUMC van and approved driver, if needed Determine if MBs will be earned or started during events | Trip Advisor with PLC input | Troop Calendar of PLC meeting dates at www.bsatroop214.us O-Council calendar of possible conflicts at www.ocscouts.org BMUMC Secretary Mary Honeycutt @ 787-0789 Troop Comm/MB Chair Jay Sprankle at troop214tc@gmail.com
D-Day -60 | 2 months before | Present semi-final plans at PLC meeting Plan and assign Troop Program segments Plan and assign trip flier creation Give verbal teasers during Troop Announcements | Trip Advisor and Trip Committee | Flier should answer Who, What, When, Where, Why, How?
D-Day -30 | 1 month before | Present final plans at PLC meeting Begin hosting Troop Program segments on topic Distribute trip fliers and post patrol sign-up sheets Begin collecting camping and event fees Ensure that untrained adult attendees take "Youth Protection" | Trip Advisor and Trip Committee | Engage multiple senses (sight, sound, etc.) during Programs "Youth Protection" online course at www.myscouting.org
D-Day -14 | 2 weeks before | Confirm bookings with campsite and event vendors Confirm scout and adult attendees and drivers Continue hosting Troop Program segments on topic | Trip Advisor and Trip Committee
D-Day -07 | 1 week before | Confirm scout and adult attendees and drivers Continue hosting Troop Program segments on topic Print trip itineraries (miles, directions, contacts) for drivers Complete Tour Permit and fax to O-Council office | Trip Advisor and Trip Committee | www.mapquest.com, www.maps.google.com Tour Permit at www.bsatroop214.us Occoneechee Council office fax @ 872-1159
D-Day -01 | 1 day before | Be available via phone for last-minute questions Obtain $100 in 5s,10s, 20s for gas fee change Get BMUMC van key 8:30am-5pm (office closed Fri pm) | Trip Advisor | BMUMC Secretary Mary Honeycutt @ 787-0789
D-Day | Fri departure | Gas up vehicle, collect gas fees, and change large bills Load Troop medical forms, first aid kits, and satellite phone Distribute trip itineraries to other drivers Share and save driver mobile phone numbers | Trip Advisor | Troop Quartermaster Hut key in Scoutmaster's office drawer Troop medical forms in ammo box in SM's office Troo first aid kits in or around SM's office, or QM Hut
D-Day +01 | Sat events | Save expense receipts: gas, fees, tolls, tips, etc. Photograph the scouts and leaders in action! Reimburse adult drivers for personal vehicle gas usage | Trip Advisor
D-Day +02 | Sun return | Save expense receipts: gas, fees, tolls, tips, etc. Photograph the scouts and leaders in action! Offload Troop gear, clean up BMUMC van if used | Trip Advisor
D-Day +03 | Mon after | Optional: slideshow of trip pictures during Program Segment Verbal trip recap during Troop Announcements Return BMUMC van key to church office, if used | Trip Advisor | BMUMC Secretary Mary Honeycutt @ 787-0789
D-Day +14 | 2 weeks after | Share CD or flash drive of trip pictures with Troop Web Master | Trip Advisor | Troop trip photos at www.bsatroop214.us
D-Day +30 | 1 month after | Share written trip recap with Troop Newsletter Editor Save records for future such trip advisors! | Trip Advisor and Trip Committee | Newsletter Editor Kathy Sprankle at genequeen@nc.rr.com

## Attendees & Fees
# | Last Name | First Name | Patrol Add rows as needed | $ Gas Fee Received @ Departure | $ Camping Fee Received in Advance | Camping Fee Payment Date | Completed & Signed Trip Form Return Date If applicable | Car Year/Make/Model, Drivers License#, $ Insurance Coverage Levels Minimum Recommended: $50K/$100K/$50K | Max# Passengers Including driver | $ Gas Repayment Returned to Driver | Notes
1 |  |  | Phoenix
2 |  |  | Phoenix
3 |  |  | Phoenix
4 |  |  | Phoenix
5 |  |  | Eagles
6 |  |  | Eagles
7 |  |  | Eagles
8 |  |  | Eagles
9 |  |  | Chuck/Panthers
10 |  |  | Chuck/Panthers
11 |  |  | Chuck/Panthers
12 |  |  | Chuck/Panthers
13 |  |  | Raiders
14 |  |  | Raiders
15 |  |  | Raiders
16 |  |  | Raiders
17 |  |  | Cobra/Generic/Arrows
18 |  |  | Cobra/Generic/Arrows
19 |  |  | Cobra/Generic/Arrows
20 |  |  | Cobra/Generic/Arrows
21 | [7 empty] | Example: BMUMC "Bus"/NC 21469214/ $100K pp/$500K p. accident/$100K prop. damage |  |  | mobile phone email address
22
23
24
25 | [7 empty] | ?
|  |  | Fee Totals: | 0 | 0 |  |  | Passengers Total: | 0
| *Grub & Grog to bring: Water bottle for weekend Bagged dinner for Fri night drive? Patrol Bfasts for Sat & Sun? Patrol Lunch for Sat only? Patrol Dinner for Sat only? |  |  | Additional $ to Bring: $XX Lunch fast food Sun only? $XX Gift shopping/vending (optional)? |  |  |  | Miscellaneous: Scout/Adult campers on "stand-by" Adult drivers on "stand-by" Unanticipated fees, tips, etc?

## Sign-up Sheets
XYZ Camp Out |  |  | Dates
Chuck/Panthers Patrol
Name | Attending | NOT Attending | Leadership Role | Notes
Alex Casey
Thomas Fair
Graham Holmes
Michael Iwanisek
Andy Lam
Robbie Proffitt
Justin Burdett
Matthew Hodnett
Matthew Kuwalik
Troy Sturdivant
SPL= Troop Senior Patrol Leader
PL = Patrol Leader
APL= Asst. Patrol Leader
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TG = Troop Guide
CA = Troop Chaplain's Aide
BU = Troop Bugler
XYZ Camp Out |  |  | Dates
Cobra/Generic/Arrows Patrol
Name | Attending | NOT Attending | Leadership Role | Notes
Stephen Frein
Brandon Hodnett
Josh Jones
Peter Michaud
Rob Sprankle
Rob Sprankle
Josh Thomas
Josh Thomas
Sean Colby
Seth Colby
Sam Gale
Joe Huergo
Kenny Jones
SPL= Troop Senior Patrol Leader
PL = Patrol Leader
APL= Asst. Patrol Leader
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TG = Troop Guide
CA = Troop Chaplain's Aide
BU = Troop Bugler
XYZ Camp Out |  |  | Dates
Raiders Patrol
Name | Attending | NOT Attending | Leadership Role | Notes
Liam Bailey
Javier Castillo
Matthew Fiely
Ross Gattis
Andy Jones
Noah Luxford
Ernesto Rivera-Saquerta
Taylor Willis
SPL= Troop Senior Patrol Leader
PL = Patrol Leader
APL= Asst. Patrol Leader
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TG = Troop Guide
CA = Troop Chaplain's Aide
BU = Troop Bugler
XYZ Camp Out |  |  | Dates
Old Goats Patrol
Name | Attending | NOT Attending | IF Driving, # Occupants Including Driver | DL # and Insurance $pp / $pa / $pd
David Burdett
Mike Casey
Frank Castillo
Bill Dvorak
Mike Fair
Joe Fiely
Sam Fouse
Don Fowler
Mike Frein
Joseph Heil
Harold Hodnett
Greg Jones
Mike Jones
John Kruse
Allan Proffitt
Tim Stammers
Stuart Thomas
John Willis
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TA = Trip Advisor (Reservations, Tour Permit, Fees, etc.)
XYZ Camp Out |  |  | Dates
Eagle Patrol
Name | Attending | NOT Attending | Leadership Role | Notes
Jonathan Babb
C.J. Hicks.
Jefferson Norwood
Ian Reetz
Derek Rose
Dylan Skiscim
SPL= Troop Senior Patrol Leader
PL = Patrol Leader
APL= Asst. Patrol Leader
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TG = Troop Guide
CA = Troop Chaplain's Aide
BU = Troop Bugler
XYZ Camp Out |  |  | Dates
Phoenix Patrol
Name | Attending | NOT Attending | Leadership Role | Notes
Burdette, Cameron
Foscato, Jake
Hixson, Ian
Vink, Cameron
SPL= Troop Senior Patrol Leader
PL = Patrol Leader
APL= Asst. Patrol Leader
GM = Patrol Grubmaster
QM = Patrol Quartermaster
TG = Troop Guide
CA = Troop Chaplain's Aide
BU = Troop Bugler